## Plan 1.0
PROJECT RadEmploy
Project Name: RadEmploy
Creator : Shakti Saini
Module |  | Start Date | End Date | Status | Acceptance
Milestone 1 |  | 2025-04-16 | 2025-05-07
Sprint 1 |  | 16 /04/2025 | 2025-04-18
Modules/Tasks | Assigned | Estimated Hours | Actual Hours | Status | Acceptance
project setup | Shakti Saini | 24
Basic signup flow Undersatnding
R & D for resume extraction using open AI
Integrate libraries to extract data from the resume with .docx ,PPT, jpeg and pdf in backend
Sprint 2 |  | 21 /04/2025 | 2025-04-25
Integrate File Parsing Libraries Implement libraries in the backend to extract data from resumes in various formats including .docx, .ppt, .jpeg, and .pdf. | Shakti Saini | 40
Design a Comprehensive Prompt for Extraction Create and integrate a well-structured prompt to extract detailed information such as education, work experience, languages, preferred employment type, skills, certifications, degrees, and years of experience. Use the extracted data to auto-fill the user profile fields.
Leverage OpenAI for Data Categorization Use OpenAI’s capabilities to intelligently extract, analyze, and categorize the required information from the resume content.
Implement Robust Error Handling Add comprehensive error handling to manage and log failed API calls and unexpected parsing issues gracefully.
Conduct Accuracy Testing Perform accuracy testing on the extracted data by comparing it with expected results or sample ground truth resumes.
Continuous Improvement with Feedback Loop Set up a feedback mechanism to refine extraction logic and prompt quality over time based on accuracy results and user feedback.
Sprint 3 |  | 28 /04/2025 | 2025-04-30
Parsed information is displayed for user review. | Shakti Saini | 24
Users can skip editing if the information is correct.
If any details are inaccurate or missing, manual editing is allowed.
Sprint 4 |  | 01 /05/2025 | 2025-05-02
Certification and licensing details (e.g., Radiology, Ultrasound Tech, X-ray Tech) are auto-filled when detected in the resume. | Shakti Saini | 16
If no relevant information is found, fields remain empty
Users can manually enter or update certification details as needed.
Sprint 5 |  | 05 /05/2025 | 2025-05-07
Users have the option to: Upload a resume immediately, or Choose to upload later / indicate no resume (e.g., for students). | Shakti Saini | 24
Uploaded resumes are parsed to auto-fill relevant details (certifications, contact info, etc.).
If no resume is uploaded, users can manually input required information.
Backend APIs handle: Resume file upload Parsing and data extraction Manual input updates and validation

## Milestone Schedule
Project Release Plan
Milestone No | Sprint | No. of resources | Start Date | End Date | Release No | Milestone Acceptance date | Actual hrs burnt | Status | Acceptance Date

## Summary
Project Start Date
Actual End Date
BDG Person
Revision History
Date | Author | Changes Details | Reference
Resource Allocation
Name | Role On Project | Alignment Date | Resource Released Date